## Sheet1
Moduls & milestone
S.No | Server Side | Milestone | Status
1 | Data analysis about project | 1week
2 | Create Database structure & serialization | 2weeks
3 | Create Database, Table, Fields & Insert Dummy data | 1week
4 | Create Folder structure, Migration to git hub | 1week
API
5 | Create user registeration with validation | 3days
6 | email verfication | 2days
7 | edit user details | 2days
8 | delete user details | 1day
9 | Create user registeration with social account(Facebook, Gmail) | 3days
10 | Create login api | 1day
11 | create login with social account(Facebook, Gmail) | 1day
12 | forget password | 2days
13 | reset password | 2days
14 | revember password | 1day
15 | change password | 1day
16 | create category | 1day
17 | edit category | 1day
18 | delete category | 1day
19 | create sub category | 1day
20 | edit sub category | 1day
21 | delete sub category | 1day
22 | create course api | 2weeks
Admin approve Course
Admin approve category
23 | edit course api | 1weeks
24 | delete course api | 3days
25 | select all course | 1day
26 | select single course | 1day
27 | create banner | 3days
28 | edit banner | 2days
29 | delete banner | 1day
30 | select category based course | 1day
31 | select subcategory based course | 1day
32 | select category & subcategory based course | 2days
33 | search category | 3days
34 | search course | 2days
35 | side bar filters | 1week
36 | subscribe | 2days
37 | Add to cart | 1week
38 | wishlist API | 3days
39 | related course list | 2days
Front End
40 | Create home page design | 1Day
41 | course page | 1Day
42 | single course page | 1Day
43 | checkout page | 1Day
44 | cart page | 1Day
45 | payment success page | 1Day
46 | payment reject page | 1Day
47 | payment cancel page | 1Day
Admin Side
48 | Login page | 1Day
49 | dashboard | 2Days
50 | models (popup) | 1Day
51 | basic front end validation | 1Day
User side
52 | login page | 1Day
53 | registration page | 2Days
54 | dashboard | 3Days
55 | wishlist design | 1Day
56 | purchase course list | 1Day
instructor Side
| Login page | 1Day
| registration page | 1Day
| dashboard | 3Days
| Create course page | 2Days
| list course page | 1Day
Back End (integrate API to front end & backend)
Admin Side
57 | create banner with backend validation | 2Days
58 | edit banner | 1Day
59 | delete banner | 1Day
60 | List the Banner | 1Day
61 | create category | 2Days
62 | edit category | 2Days
63 | delete category | 1Day
64 | create subcategory | 2Days
65 | edit subcategory | 2Days
66 | deletesubcategory | 1Day
67 | create course | 3Days
68 | edit course | 2Days
69 | delete course | 1Day
User Side
70 | Integrate home page | 2Days
71 | Integrate search course | 1Day
72 | Integrate login page with front end validation | 2Days
73 | Integrate register page with front end validation | 3Days
74 | Integrate course page | 1Day
75 | Integrate single course page | 1Day