## Courses
Moduls & milestone
S.No | Server Side | Milestone | Status
1 | Data analysis about project | 1week
2 | Create Database structure & serialization | 2weeks
3 | Create Database, Table, Fields & Insert Dummy data | 1week
4 | Create Folder structure, Migration to git hub | 1week
API
5 | Create user registeration with validation | 3days
6 | email verfication | 2days
7 | edit user details | 2days
8 | delete user details | 1day
9 | Create user registeration with social account(Facebook, Gmail) | 3days
10 | Create login api | 1day
11 | create login with social account(Facebook, Gmail) | 1day
12 | forget password | 2days
13 | reset password | 2days
14 | revember password | 1day
15 | change password | 1day
16 | create category | 1day
17 | edit category | 1day
18 | delete category | 1day
19 | create sub category | 1day
20 | edit sub category | 1day
21 | delete sub category | 1day
22 | create course api | 2weeks
23 | Admin approve Course | 2days
24 | Admin approve category | 2days
25 | edit course api | 1weeks
26 | delete course api | 3days
27 | select all course | 1day
28 | select single course | 1day
29 | create banner | 3days
30 | edit banner | 2days
31 | delete banner | 1day
32 | select category based course | 1day
33 | select subcategory based course | 1day
34 | select category & subcategory based course | 2days
35 | search category | 3days
36 | search course | 2days
37 | side bar filters | 1week
38 | subscribe | 2days
39 | Add to cart | 1week
40 | wishlist API | 3days
41 | related course list | 2days
42 | user list | 2days
43 | delete user | 1day
44 | instructor list | 2days
45 | instructor delete | 1day
46 | create wallet for instructor | 5Days
47 | wallet update | 2days
48 | display wallet | 1day
49 | purchase course list | 2days
50 | create rating for course & review | 1week
51 | rating display with commends | 3days
52 | replay for rating | 3days
53 | Place the order (course) | 1week
54 | purchase order amount details | 1week
55 | instructor commition details | 1week
56 | weekly report | 1week
57 | monthly report | 1week
58 | yearly report | 1week
Front End
59 | Create home page design | 1Day
60 | course page | 1Day
61 | single course page | 1Day
62 | checkout page | 1Day
63 | cart page | 1Day
64 | payment success page | 1Day
65 | payment reject page | 1Day
66 | payment cancel page | 1Day
Admin Side
67 | Login page | 1Day
68 | dashboard | 2Days
69 | models (popup) | 1Day
70 | basic front end validation | 1Day
User side
71 | login page | 1Day
72 | registration page | 2Days
73 | dashboard | 3Days
74 | wishlist design | 1Day
75 | purchase course list | 1Day
instructor Side
76 | Login page | 1Day
77 | registration page | 1Day
78 | dashboard | 3Days
79 | Create course page | 2Days
80 | list course page | 1Day
81 | display wallet details | 2Days
Back End (integrate API to front end & backend)
Admin Side
82 | create banner with backend validation | 2Days
83 | edit banner | 1Day
84 | delete banner | 1Day
85 | List the Banner | 1Day
86 | create category | 2Days
87 | edit category | 2Days
88 | delete category | 1Day
89 | create subcategory | 2Days
90 | edit subcategory | 2Days
91 | deletesubcategory | 1Day
92 | create course | 3Days
93 | edit course | 2Days
94 | delete course | 1Day
95 | User details | 2Days
96 | Approve course | 2Days
97 | Approve category | 2Days
98 | Approve subcategory | 1Day
99 | instructor details | 2Days
100 | purchase details | 2Days
101 | purchase course details | 2Days
102 | Rating details | 2Days
103 | rating replay | 3Days
104 | instructor comition details | 2Days
105 | instructor amount pay using payment gateway | 5days
106 | integrate weekly report | 3Days
107 | integrate monthly report | 2Days
108 | integrate yearly report | 2Days
109 | integrate dashboard | 2Weeks
User Side
110 | Integrate home page | 2Days
111 | Integrate search course | 1Day
112 | Integrate login page with front end validation | 2Days
113 | Integrate register page with front end validation | 3Days
114 | Integrate course page | 1Day
115 | Integrate single course page | 1Day
116 | Wishlist | 2Days
117 | purchse list | 2Days
118 | view purchse course | 3Days
119 | comment about course (rating) | 4days
120 | profile update | 1week
121 | Payment Integrate | 1week
Instructor
122 | create category | 2Days
123 | edit category | 2Days
124 | category list | 2Days
125 | create subcategory | 2Days
126 | edit subcategory | 2Days
127 | Subcategory list | 2Days
128 | create course | 3Days
129 | edit course | 3Days
130 | view our course rating only | 2Days
131 | replay rating our courses only | 2Days
132 | wallet datails | 3Days
133 | integrate dashboard | 4days

## Sheet2
Courses
Admin | User / Student | instructor
Login | Wishlist | Login
Register | Purchase list | Register
dashboard | Add to cart | dashboard
Course |  | Course
create |  | create
Edit |  | Edit
Delete |  | category
Approve |  | create
category |  | Edit
create |  | Sub Category
Edit |  | create
Delete |  | Edit
Approve
Sub Category
create
Edit
Delete
Approve